# Comprehensive Antibiogram Toolkit: Phase 1

# Sample Timeline

| Task complete | Year |  |
| --- | --- | --- |
|  | Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
|  | Task 1: Assessment and Planning |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Complete the Nursing Home Readiness and Resources Assessment |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Distribute the Prescribing Clinician Survey and tabulate results |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Establish the clinical laboratory contact |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Establish the local hospital and Emergency Department (ED) contact |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Compile results from assessments and survey |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Present findings to nursing home/corporate management |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Task 2: Antibiogram Development |
|  | Begin or continue discussions with the laboratory |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Establish whether laboratory or nursing home will develop antibiogram |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Request laboratory data as needed |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Develop draft antibiogram |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Modify antibiogram as needed |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Task 3: Antibiogram Implementation |
|  | Determine whether a new policy is required; if so, draft it |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Write procedures for antibiogram program |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Have management review policy/procedure; modify as needed |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Roll out new policy/procedure |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Decide on dissemination method for prescribing clinicians and ED physicians |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Review/edit training materials |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Schedule and complete training for prescribing clinicians |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Schedule and complete training for nurses and nursing support staff |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Roll out antibiogram program |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Task 4: Monitoring |
|  | Add to quality improvement program (i.e., determine best tracking method) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Gather baseline data |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Monitor antibiotic use on a monthly basis |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Review/edit feedback survey |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Administer feedback survey |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Make revisions to antibiogram based on user feedback |  |  |  |  |  |  |  |  |  |  |  |  |